## PBL
	Pomotux by Team 8

						Optional		Optional
	User story		Size (ideal hours)	Size (hours)			Size (actual)
id	Title	Description	Estimate	Actual	Priority (1-3)	Sprint id	LOC	Acceptance test	Notes
Unique id for each user story	A short & descriptive title for each user story	A description of the intent of the user story	You guesstimate of the work effort in ideal hours (4-10)	You actual (completed when user story finished)	1 = must have, 2 = ought to have, 3= nice to have	In which sprint the development takes/took place	Recorded after completion of each user story	A reference to the acceptance test (or if short enough, can be here)	Further notes about the user story
1	Pomodoro Length	By changing a value, user decides how long a pomodoro should last	4		2
2	Inspect AIS	User can see the list of the activities he shuold do	10	8	1	1			Decision of the data structure that holds the activities and how to manage their persistence
3	Insert Activity	A user can insert an activity in the "Activity Inventory Sheet", as the activity comes up	10	15	1	2			Highly depends on 2
4	Modify Activity	A user can edit an activity from the "Activity Inventory Sheet"	10	5	1	3			Highly depends on 2
5	Delete Activity	A user can delete an activity in the "Activity Inventory Sheet"	10	13	1	2			Highly depends on 2
6	Inspect TDTS	User can inspect the list of the activities he should perform today	8	4	1	1
7	Fill TDTS	The user can move an activity from the "Activity Inventory Sheet" to the "To Do Today Sheet"	6	10	1	3
8	Order TDTS	User can prioritize the activities of the "To Do Today Sheet", as they must be done sequentially	6	11	1	3
9	Start a Pomodoro	User begins/continues the first available activity of the "To Do Today Sheet". The timer starts and shows up	5	10	1
10	Break a Pomodoro	User decides to interrupt the current Pomodoro	4		1
11	Finish a Pomodoro	The pomodoro finishes, user is alerted to make a short break	8		1
12	Finish an Activity	User decides that his activity is finished, the current activity is show as finished and marked as finished in the "Activity Inventory Sheet", the next activity is selected	10	16	1	3			Could be complex
13	Postpone an Activity	User can postpone a task of the "To Do Today Sheet". This does not remove it from the "Activity Inventory Sheet", as it must be done on another day	6	1	1	3
14	Long Break	After 4 completed pomodoro, user is alerted to make a long break	4		1
15	No. Int Interruptions	User sees how many internal interruptions he faced during a pomodoro	3		2
16	Register Int Interruptions	User can quickly write the interruption in the Activity Inventory Sheet, to turn it in a activity	10		2
17	No. Ext Interruptions	User sees how many internal interruptions he faced during a pomodoro	1		2				Depends on 15
18	Register Ext Interruption	User can quickly write the external interruption in the Activity Inventory Sheet, to turn it in a activity	2		2				Depends on 16
19	Pomodoro Ring	When a pomodoro finishes, a sound is played	5		3
20	Pomodoro Ring Set	User can decide the sound to be heard when a pomodoro finishes	8		3
21	Team Support	More users have the same AIS but different TDTS	8		4!
22	Gui Support for Activities	Not a user story but a reminder	62
23	Gui Support for Pomodoros	Not a user story, it's a task container	20
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47

## Sprint1
			(ideal hours)		optional	optional
User story id	task id	task description	size estimate (0,5-2h)	size actual	location in code	notes
2	2.1'	Data structure of AIS	9	5
2	2.2'	Printout of some dummy population data	1	3
6	6.1'	Data structure of TDTS	2	3
6	6.2'	Printout of some dummy population data	1	1

## Sprint2
			(ideal hours)		optional	optional
User story id	task id	task description	size estimate (0,5-2h)	size actual	location in code	notes
3	3.1'	provide getters and setters for AIS	3	5
	3.2'	create a method for receiving an Activity from AIS given its ID	5	6
	3.3'	create a method for inserting an Activity in AIS	5	6
5	5.1'	create a method for deleting permanently an Activity	10	13

## Sprint3
			(ideal hours)		optional	optional
User story id	task id	task description	size estimate (0,5-2h)	size actual	location in code	notes
7	7.1'	Provide a method that Copies an Activity from “InsertActivity” to “PickUpActivity”	6	10
8	8.1'	Provide a method to push up an Activity in the TDTS	6	10
	8.2'	Provide a method to push down an Activity in the TDTS	6	1
12	12.1'	Provide a method that sets an Activity As Finished. This should unlink it from TDTS but NOT from AIS	5	8
	12.2'	Make shure that TDTS does not show activities that are finished.	5	8
4	4.1'	create a method for modify an Activity given its ID	10	5
13	13.1'	Provide a method to remove the activity from TTS without loosing its information	6	1

## Sprint4
			(ideal hours)		optional	optional
User story id	task id	task description	size estimate (0,5-2h)	size actual	location in code	notes
22	22.1'	GUI for Inspect AIS	10
	22.2'	GUI for Insert Activity	8
	22.3'	GUI for Delete Activity	4
	22.4'	GUI for Modify Activity	8
	22.5'	GUI for TTS	10
	22.6'	GUI for fill TTS	8
	22.7'	GUI for Order Activities	8
	22.8'	GUI for Finish Activity	6

## Sprint5
			(ideal hours)		optional	optional
User story id	task id	task description	size estimate (0,5-2h)	size actual	location in code	notes
22	22.1'	GUI for Inspect AIS	10	10
	22.2'	GUI for Insert Activity	8	2
	22.3'	GUI for Delete Activity	4	1
	22.4'	GUI for Modify Activity	8	1
	22.5'	GUI for TTS	10	13
	22.6'	GUI for fill TTS	8	2
	22.7'	GUI for Order Activities	8	4
	22.8'	GUI for Finish Activity	6	2
9,23	9.1'/23.1'	Implement a class for Pomodoro using QT	2	8
	9.2'/23.2	Make the class fully independent to be used as a widget	2	1
	9.3'/23.3	Unify TTS and Pomodoro classes, to be used together	1	1
10	10.1'	Provide a method to handle a Pomodoro interruption	1	2
11	11.1'	Write in TTS (Gui) a method that intercepts Pomodoro signals	2	1
	11.2'	Write in TTS (Gui) a method to create a new window to alert the user to break	2	1
12	12.1'	Provide a method to set the activity as finished in the GUI. Tables should be refreshed	/	3
13	13,1'	Provide a method in the GUI to unlink the activity from TTS, refresh tables. Even if Pomodoro is running	/	3
14	14.1'	Use a class attribute integer in TTS Gui. Every (multiple of) 4 pomodoro the alert for a short break becomes an alert for a long break	4	2

## Sprint 6
			(ideal hours)		optional	optional
User story id	task id	task description	size estimate (0,5-2h)	size actual	location in code	notes
1	1.1'	Provide a new window for the Options	2
	1.2'	Try to have a configuration file to store the options	5
	1.3'	Insert in the Option window the possibility to change Pomodoro Length (minutes)	2
16,18	16.1',18.1'	Insert in TTS (gui) a shortcut for the insertion of a New Activity of AIS (gui).	10
16,18	16.2',18.2'	The method created before should handle the case for which a Pomodoro is Running.	1
15,17	15.1,17.1'	User should see an integer number representing the number of interruptions he faced today.	1
19	19.1'	Play a sound when Pomodoro Finishes	5

## Sprint 7
			(ideal hours)		optional	optional
User story id	task id	task description	size estimate (0,5-2h)	size actual	location in code	notes